## Sheet1
Milestone | Related Tasks | Completion Date
Planning and Organization | Scheduling | 2020-06-05
Team Organization and Assignments
Standards Development
Research and Functionality Description | Adding Modules/Function to Spec | 2020-06-10
Learning Verilog
Requirements |  | 2020-06-11
Module Development |  | 2020-06-12
Module Verification |  | 2020-06-16
Functional Verification (Top Level) |  | 2020-06-17
Synthesis and FPGA Implementation |  | 2020-06-18
Final |  | 2020-06-19